## Ideas
Weight | Name | Description
6 | Set up VM | Set up a VM for the team to use for deploying our app using a cloud service such as GCP or Azure.
2 | Set up NGINX | Set up the webserver on the VM
2 | Install backend stuff (Python, Flask, libraries, etc) | Also create an install script for automating this process (use the apt package manager)
1 | Design basic UI | Design the basic website/UI layout
2 | Implement a Flask web server | Create a basic flask server
4 | Create a basic webpage (HTML/CSS) | Create a basic webpage so something actually shows up when you navigate to the web app. Add CSS (use bootstrap). Install jQuery
3 | Setup Basic React + Node | Add react
2 | Research the stack | Each team member should familiarize themselves with the stack (Flask, React, etc)
3 | Set up HTTPS certificate | Self sign and configure an HTTPS certificate (likely involves research)
2 | Documentation for how to use config files and where to put them | Not too sure what this is for but it was in the sprint 4 deliverables (figure out what we're doing here)
1 | Documentation for how to get everything up and running | How to run the install script, run the server, etc
1 | Document the URL/IP of the web app | This won't take long, but since it's a deliverable we should have a task for it so we don't forget
2 | Look into CI/CD | Greg suggested we do this
2 | Research JS libraries for helping with graphing courses | Greg suggested we do this
2 | Docker research? | We might want to do some research on using Docker with a Flask server for later
2 | Implement docker? (stretch) | We won't get marks for this, but it will make our lives easier probably. We can develop on Docker, but the final product should not be expected to require Docker
1 | Research what SQL type and cloud service we want to use for our database (stretch) | Database is not required yet, but we might want to start thinking about this. Firebase might be a good choice because it integrates well with GCP
Set up Gunicorn

## Time Tracking
Name: | Dogu Gerger |  | Ethan Rowan |  | Sahil Gogia |  | Kalindu Kehel Baddarage |  | Ameer Mushani |  | Nash Rudiak |  | Cameron Norrie
Discord name: | dgerger |  | Ethan |  | been |  | Synapse |  | Ameer M |  | Nash Rudiak |  | Cameron Norrie
| 2 | Sprint initial meeting | 6 | Set up the VM | 3 | Sprint initial meeting 2 | 3 | Sprint initial meeting 2 | 3 | Sprint initial meeting 2 | 2 | Sprint initial meeting | 3 | Sprint initial meeting 2
| 6 | Assisted in NGINX development | 2 | Sprint initial meeting | 5 | Assisted in react app setup | 5 | Assisted in react app setup | 5 | Setup Basic React + Node | 5 | Assisted in NGINX development | 5 | Assisted in react app setup
|  |  | 1 | Set up NGINX | 2 | Reviewing & understanding new project structure | 3 | Research stack | 1 | Presentation | 1 | Small Flask application | 3 | Research stack
|  |  | 5 | Applied Flask to NGINX server | 7 | Developing the UI for the courseloader webpage | 1 | Presentation | 2 | End of sprint meeting | 4 | Assisted in react app setup | 2 | End of sprint meeting
|  |  | 8 | Improved project structure and fixed issues regarding nginx | 1 | Creating the presentation slide | 2 | End of sprint meeting | 2 | MR Review | 4 | Helped improve project structure | 1 | Presentation
|  |  | 2 | Set up HTTPS | 6 | Learned about some web dev concepts |  |  | 5 | JSX improvments | 6 | Implementing and researching JS calendar in React | 3 | Installing/setting up GCP CLI tool on my system, understanding new project structure
[9 empty] | 1 | React-bootstrap setup
Total | 8 |  | 24 |  | 24 |  | 14 |  | 19 |  | 22 |  | 17