## Tasks
Weight | Name | Description
4 | Sprint 3 planning meeting | A meeting to plan out the sprint will be held on Monday.
2 | Sprint 3 code review meeting on Sunday | A final meeting to review the code, held on Sunday.
1 | Slide creation | Add at least 1 slide to the presentation, explaining what you did during this sprint.
1 | Lowest day | Create a function which determines which day contains the least amount of activity.
1 | Check conflicts | Create a function to check if the course has conflicts. (Hint: same function as plotting a course, but remove all statements that show something like making a border or colouring a box)
2 | Find courses based on day | Find courses that have a lecture on the day, and check if a conflict occurs. Will return an array which has all courses that cause no conflicts and have something on that day. The array should only contain the amount of blank entries (Eg, if 2 courses are filled out, then give 3 suggestions).
1 | Print suggestions | Print out an array of courses given. It can be a simple text box, a message box that pops up, or even something more complicated.
1 | Add course | Given the list of suggested courses, if the user wants they can immediately add the course.
2 | Documentation for Readme | Add some documentation explaining how to use the suggestion feature
3 | Documentation for Wiki | Create thorough documentation on the Wiki page explaining how the suggestion feature works.
2 | Favourable time | Create a function to determine which times have the most frequency: Morning, Afternoon, Evening.
2 | Check expansion | Expand the Check Conflicts function to choose courses which exclude the highest day and are within their favourable time range (Eg, times in the morning on Tuesday)
1 | Highest Day | Create a function to determine which day contains the most amount of activity.
1 | Re-obtain information | Develop a function to re-find courses previously entered to gain their information. Can return a line number or attempt to return all the data.
2 | Create suggestion UI | Make the UI for suggestions look better.
2 | Preview course | Create a function which will show what the schedule would look like with suggestions in. Will not actually be entered in.
2 | Add section functionality | Expand previous functions to not just search for a course, but also the best section.
2 | Change suggestion format | Allow the user to change what is an "optimal" schedule (Eg, instead of spread out have it all be close to the beginnning) (add documentation for adding new suggestions).
1 | Separate the VBA code from the spreadsheet | Create a new folder holding simple text documents, to make analyzing Merge Requests easier.
1 | Merge Request Review | Any time spent to reviewing a merge request can be added to this task.
1 | Toggle Hide Exams | Add an option the user can click/activate that will cause the program to not print out any exam information.
2 | Ignore List | Create a option to cause the program to exclude/ignore certain days (Eg, Friday you might want free, so it will choose courses that are not on Friday)
2 | Ignore Time | Create a option to cause the program to exclude/ignore certain time e.g 8:30AM
2 | Create seach for tuesday/thurday free | Create a function to get courses that do not occur on tuesday or Thursday. | 𐐘 | ඞ
2 | Create search for Friday free | Create a function to get courses that do not occur on Friday.
2 | Create Search for no early mornings | Nothing scheduled at 8:30 or any arbitrary time we choose.
2 | Create search for no afternoon classes | Add an option to remove the ability for the suggester to choose afternoon classes.
2 | Create search for no evening classes | Add an option to remove the ability for the suggester to choose evening classes.
1 | Extra documentation | If you add an extra method, you are required to add your own documentation to the wiki and readme.
4 | Searches work together (stretch goal) | Add functionality for searches to work together.

## Progress
Name: | Dogu Gerger |  | Ethan Rowan |  | Sahil Gogia |  | Kalindu Kehel Baddarage |  | Ameer Mushani |  | Nash Rudiak |  | Cameron Norrie
Discord name: | dgerger |  | Ethan |  | been |  | Synapse |  | Ammer M |  | Nash Rudiak |  | Cameron Norrie
| 2 | Meeting | 2 | Meeting | 2 | Meeting | 2 | Meeting | 2 | Meeting | 2 | Meeting
|  |  | 4 | Research and importing VBA code to files | 5 | Printing Courses (Pair) | 2 | Code Review | 2 | Debugging check conflicts | 2 | Pre-planning for meeting
| 3 | Documentation | 2 | Debugging check conflicts | 2 | Optimization Planning + Bug fixing (Paired) | 2 | Presentation creation | 7 | No Tuesday/Thursday + No Fridays | 1 | Toggle hide exams
| 2 | Wiki Documentation | 6 | Printing Courses (Pair) | 7 | Optimization Planning + Bug fixing + getNoEvenings (Paired) | 3 | Documentation | 1 | Bug fixing Tues/Thurs | 1 | Lowest Day
| 2 | Rubberneck automated testing research | 3 | Find courses Start and UI | 2 | Code Review | 2 | Wiki Documentation | 2 | Tues/Thurs fixed edge cases | 3 | Check Conflicts
| 2 | Rubberduck automated testing implementation | 1 | Feedback for No early mornings. | 1 | Slide creation | 2 | Rubberneck automated testing research | 2 | Friday free implementation and IgnoreTime | 1 | Check conflict bug fixing and documentation
|  |  | 7 | Optimization Planning + Bug fixing + getNoEvenings (Paired) | 1 | Testing the program | 2 | Rubberduck automated testing implementation | 1 | No early mornings implementation | 4 | Printing Courses (Pair)
|  |  | 2 | Code Review |  |  |  |  | 1 | Implemented fixes for No Early Mornings | 1 | Bug fixing Tues/Thurs
|  |  | 1 | Slide creation |  |  |  |  | 1 | Resolving merge conflicts | 4 | Find courses based on day
[9 empty] | 2 | Code Review | 5 | Optimization Planning + Bug fixing + getNoEvenings (Paired)
[9 empty] | 1 | Slide creation | 2 | Code Review
| 11 |  | 28 |  | 20 |  | 15 |  | 22 |  | 26 |  | 0
* Additional untracked time for slideshow creation, time spent unknown